## 30.05.2025
RSO meeting at OHS Conference Hall
Date & Time: -30.05.2025 (3:00PM)
Chaired By: - Mr. Lalit Kumar Goyal
Sl. No. | Name | Mail id | Mob. No. | Department | Attendance
1 | Lalit Kumar Goyal | lalit.goyal@jindalsteel.com | 9827477098 | CAC | P
2 | Dhirendra Prasad Kushwaha | dhirendra.kushwaha@jindalsteel.com | 8827477099 | CME & HESE | A
3 | Rajeev Soni | rajeev.soni@jindalsteelodisha.com | 9777449834 | OHS | A
Certified Rso from Department
4 | Mandeep Rajput | mandeep.rajput@jindalsteel.com | 9109137541 | BF # 2 | P
5 | Bhishma Patel | bhisma.patel@jindalsteel.com | 8827427237 | Plate Mill | A
6 | Saurabh Tiwari | saurabh.tiwari@jindalsteel.com | 9425522401 | BF # 1 | A
7 | Nikhilesh Gawhade | nikhilesh.gawhade@jindalsteel.com | 9109979148 | SMS # 3 | A
8 | S Mohan Iyer | mohan.iyer@jindalsteel.com | 9109979175 | SMS # 2 | P
9 | Ritesh Rai | ritesh.rai@jindalsteel.com | 8827477306 | Sinter Plant | P
10 | Suraj Yadav | suraj.yadav@jindalsteel.com | 9109956841 | Plate Mill | A
11 | Sagar Vinayak Wanve | sagar.wanve@jindalsteel.com | 9109979042 | Plate Mill | A
12 | Kanhaiya Maurya | kanhiya.maurya@jindalsteel.com | 8827394930 | Power Plant | P
13 | Alok Agarwal | alok.agrawal@jindalsteel .com | 9109130430 | TSD (BF# 2 - Lab) | P
14 | Simanchal Panda | simanchala.panda@jindalsteel.com | 9109979088 | OHS - Representative | P
15 | Ranjeet Kumar | ranjeet.kumar1@jindalsteel.com | 8827478305 | SMS # 3 | P
Minutes Of Meeting
Sl. No. | Meetings Points | Action Points | Target Date | Status | Action By | Remark
1 | Meeting Frequency | Monthly | Next Meeting 2'nd week of June 2025 |  | Mohan Iyer
2 | SSR report for July-Dec 2024 | To be submitted in elora | 15.01.2025 | Done | Simanchal Panda | Nest SSR to be uploaded in elora in July 2025. All departments to email their departmental SSR to Mr. Simanchal Panda by next meeting in June
3 | Old 9mCi 4 nos. Radioactive sources of SMS-2 to be disposed off | 1. Extraction of old source rods from old shields & shifting to transport shield 2. Wipe test 3. Disposal | 1.15.02.2025 2. 28.02.2025 3. 31.03.2025 | Old radioactive sources transferred to new transport shield. NOC received for export of sources | Mohan Iyer | WO made for extraction & disposal of old sources. To be executed by 30.06.2025
4 | Old 4mCi 6 nos. Radioactive sources of SMS-3 to be disposed off | 1. Extraction of old source rods from old shields & shifting to transport shield 2. Wipe test 3. Disposal | 1. NA 2. NA 3. 31.03.2025 | Old radioactive sources transferred to new transport shield. NOC received for export of sources | Nikhilesh & Ranjeet | WO made for extraction & disposal of old sources. To be executed by 30.06.2025
5 | New Cs-137 to be procured for SMS-3 Combi caster | Instead of Cs 137 source from Ramon Science, sources are being procured from Berthold & expected to be delivered by Dec 2024 | 31.03.2025 | Done | Mr. Nikhilesh & Mr. Ranjeet | New Co-60 Berthold sources taken in line in Feb 2025
6 | TLD badges | Phase # 1 - TLD badges to be purchased for SMS-2, (3 Nos) Phase # 2 - TLD badges to be purchased for BF, SMS3, Sinter, Coal Washery | 30.06.2025 | 1. PO made for SMS-2 2. SR made for Sinter Plant 3. SR to be made for rest departments 4. Offer taken from Pulse Echo for Gamma radiation electronic TLD badge | Mandeep, Sanjay & Mr. Nikhilesh, Akhilesh
7 | Training Module | Radiation Safety Aspects | 3'rd week of June 2025 |  | Mr. Kanhiya Mourya & Mohan Iyer | Mould operator to be arranged for training Mr. Mohan & Mr. Nikhilesh
8 | Survey Meter | Only SMS # 2 & 3 registered in e-LORA Following departments to register their departmental survey meters in Elora 1. Blast Furnace 2. Coal Washery 3. Power Plant | BF-2: 30.06.2025 Coal Washery: 30.06.2025, PP: 30.06.2025 | Addition in Elora pending | 1. Mandeep Singh Rajput 2. Suraj Yadav 3. Kanhaiya Maurya | Calibration validity of survey meters of BF about to expire in Oct 2024 so to be added after calibartion Calibration validity of survey meters of Coal Washery is valid til April 2025 so to be added after re-calibration

## 23.10.2025
RSO meeting at SMS-3 Conference Room
Date & Time: -23.10.2025 (5.30 PM - 6.30 PM)
Chaired By: - Mr. Lalit Kumar Goyal
Sl. No. | Name | Mail id | Mob. No. | Department | Attendance
1 | Lalit Kumar Goyal | lalit.goyal@jindalsteel.com | 9827477098 | CAC | P
2 | Dhirendra Prasad Kushwaha | dhirendra.kushwaha@jindalsteel.com | 8827477099 | CME & HESE | A
Certified Rso from Department
3 | Mandeep Rajput | mandeep.rajput@jindalsteel.com | 9109137541 | BF # 2 | A
4 | Bhishma Patel | bhisma.patel@jindalsteel.com | 8827427237 | BF-1 | A
5 | Saurabh Tiwari | saurabh.tiwari@jindalsteel.com | 9425522401 | BF # 1 | A
7 | Nikhilesh Gawhade | nikhilesh.gawhade@jindalsteel.com | 9109979148 | SMS # 3 | p
9 | Ritesh Rai | ritesh.rai@jindalsteel.com | 8827477306 | Sinter Plant | P
10 | Suraj Yadav | suraj.yadav@jindalsteel.com | 9109956841 | Plate Mill | A
11 | Sagar Vinayak Wanve | sagar.wanve@jindalsteel.com | 9109979042 | Plate Mill | A
12 | Kanhaiya Maurya | kanhiya.maurya@jindalsteel.com | 8827394930 | Power Plant | P
13 | Alok Agarwal | alok.agrawal@jindalsteel .com | 9109130430 | TSD (BF# 2 - Lab) | A
14 | Simanchal Panda | simanchala.panda@jindalsteel.com | 9109979088 | OHS - Representative | P
15 | Ranjeet Kumar | ranjeet.kumar1@jindalsteel.com | 8827478305 | SMS # 3 | A
Minutes Of Meeting
Sl. No. | Meetings Points | Action Points | Target Date | Status | Action By | Remark
1 | Meeting Frequency | Monthly | 2nd Wednesday November |  | Simanchal Panda
2 | SSR report for Jan-June2025 | To be submitted in elora | 25.10.2025 |  | Simanchal Panda | TOP PRIORITY
3 | New RSO registration along with finalization of list | NFA to be raised | 30.10.2025 |  | Simanchal Panda | DEPT: SMS-2 , (KEWAT AND HEMANT)/ COAL WASHERY/ SAFETY Mohan Iyer to be removed from portal as per RSO procedure.
4 | Old 9mCi 4 nos. Radioactive sources of SMS-2 to be disposed off | 1. Extraction of old source rods from old shields & shifting to transport shield 2. Wipe test 3. Disposal | 1.15.02.2025 2. 28.02.2025 3. 31.03.2025 | Disposed done | Nikhilesh | Report to be uploaded and circulated
5 | Old 4mCi 6 nos. Radioactive sources of SMS-3 to be disposed off | 1. Extraction of old source rods from old shields & shifting to transport shield 2. Wipe test 3. Disposal | 1. NA 2. NA 3. 31.03.2025 | Disposed done | Nikhilesh | Report to be uploaded and circulated
6 | New Cobalt-60 to be procured for SMS-3 Combi caster and disposal of Cs-137 | 1. Extraction of old source rods from old shields & shifting to transport shield 2. Wipe test 3. Disposal | 10.04.2026 | 1.New cobalt procured and used. 2. SR to be prepared for disposal of old source | Mr. Nikhilesh & Mr. Ranjeet | Road map to be circulated.
7 | TLD badges | TLD badges to be purchased for SMS-2, BF 1&2, SMS3, Sinter, Coal Washery,Power Plant- 10 NOs | 10.11.2025 | Fresh offer to be collected form vendors. Lalit Goyal sir will provide the vedor details | Mr. Kanhiya Mourya & Nikhlesh | company name : SP Equipment 8878000350- Parag Patidar ( Any issure related to Elora to be resolved)
8 | Training Module | Radiation Safety Aspects | 25.10.2025 |  | Mr. Kanhiya Mourya | Mould operator to be arranged for training Mr. Nikhilesh
9 | Survey Meter | List of Survey meter to be prepared along with caliberation certificate | 25.10.2025 |  | Simanchal Panda | All RSO to be provided the details

## NUCLEONIC GAUGES
LIST OF NUCLEONIC GAUGES IN JSPL
(As on date - 23-03-2026 )
S.N. | Make | Model | Gauge Sr.No. | Source | Qty. | Activity with Date | Installation Date | Location | Installed in the Plant | NOC No. | Status of Gauge | Contact Person
1 | Berthold Technologies Geramny | LB-352 | 409-04-20 /39612-011-10020,PB200 | Co-60 | 1 | 6X1702 MBq (46mCi) | 25.12.2021 | Billet Caster | SMSII | CG-33233-RF-NGD-029 | In Use | Mr. Lalit Goyal
2 | Berthold Technologies Geramny | LB-352 | 410-04-20 /39612-011-10023,PB203 | Co-60 | 1 | 6X1702 MBq (46mCi) | 25.12.2021 | Billet Caster | SMSII | CG-33233-RF-NGD-030 | In Use | Mr. Lalit Goyal
3 | Berthold Technologies Geramny | LB-352 | 411-04-20 /39612-011-10019,PB200 | Co-60 | 1 | 6X1702 MBq (46mCi) | 25.12.2021 | Billet Caster | SMSII | CG-33233-RF-NGD-031 | In Use | Mr. Lalit Goyal
4 | Berthold Technologies Geramny | LB-352 | 412-04-20 /39612-011-10024,PB203 | Co-60 | 1 | 6X1702 MBq (46mCi) | 25.12.2021 | Billet Caster | SMSII | CG-33233-RF-NGD-032 | In Use | Mr. Lalit Goyal
5 | Berthold Technologies Geramny | LB-352 | 413-04-20 /39612-011-10022,PB203 | Co-60 | 1 | 6X1702 MBq (46mCi) | 25.12.2021 | Billet Caster | SMSII | CG-33233-RF-NGD-033 | In Use | Mr. Lalit Goyal
6 | Berthold Technologies Geramny | LB-352 | 1247-07-13 | Co-60 | 1 | 4X1702 MBq (46mCi) | 10.09.2013 | Billet Caster | SMSII | AERB/RSD/NG/NR 250/2012/15047 | In Use | Mr.Prasanta kumar mishra
7 | Berthold Technologies Geramny | LB-352 | 1243-07-13 1244-07-13 1245-07-13 1246-07-13 | Co-60 | 4 | 4X333 MBq (9mCi) | 09.09.2013 | Combi caster | SMSII | AERB/RSD/NG/NR 250/2012/15047 | In Use | Mr.Prasanta kumar mishra
8 | RAMON Science & Technology, China | RAMSSK-06 |  | Cs-137 | 4 | 4X2.59 GBq (70mCi) | 2008-12-12 | Combi caster | SMSIII | AERB/RSD/NG/NR 250/2008/2285 | In Use | Mr. SAN Tiwari
9 | Berthold Technologies Geramny | LB-352 |  | Co-60 | 6 | 6X148 MBq (4mCi) | 2010-06-04 | Billet Caster | SMSIII | AERB/RSD/NG/NR 250/2010/4791 | In Use | Mr. SAN Tiwari
10 | Berthold Technologies Geramny | LB-350 |  | Am241-Be | 4 | 4 X 11.1GBq (300 mCi) | 2005-09-13 | Coal Bunkers | BF2 | AERB/RSD/NG/NR 250/2005/7406 | In Use | Mr. R K Gupta
11 | Berthold Technologies Geramny | LB-441 |  | Co-60 | 2 | 2X1.11 GBq (30mCi) | 2005-09-13 | Coal Bunkers | BF2 | AERB/RSD/NG/NR 250/2005/7406 | In Use | Mr. RK Gupta
12 | Thermo Fischer Scientific, USA | 5201 |  | Cs-137 | 4 | 4 X 370 MBq (10 mCi) | 2009-07-21 | Ash Silo | PP-1&2 | AERB/RSD/NG/NR 250/2009/3627 | In Use | Mr. Gitesh Kr. Ambasta,
13 | Berthold Technologies Germany | Model – LB 350 With Probe – LB7410 | Sr. No. 664-04-06 | Am241-Be | 1 | 11.1GBq / 300 mCi Dt : 28.06.2006 | 2006-10-27 | Coke Bunker No.18 Sinter Plant | Sinter Plant | AERB/RSD/NG/NR250/2006/3122 | In Use | Mr. RK Gupta
14 | Berthold Technologies Germany | Model – LB 350 With Probe – LB7410 | Sr. No. 663-04-06 | Am241-Be | 1 | 11.1GBq / 300 mCi Dt : 28.06.2006 | 2006-10-27 | Coke Bunker No.19 Sinter Plant | Sinter Plant | AERB/RSD/NG/NR250/2006/3122 | In Use | Mr. RK Gupta
15 | Pentax engineering | PGH20 | 437 | Cs-137 | 1 | 250mci, 09-07-2002 | 2002-03-08 | HMC delivery line | Coal washery-2 | AERB/445/TAC/NG/07/017R-3/2002/22.85,Dt 8.3.2002 | In Use | Mr. B.Srinivas
16 | Pentax engineering | PGH20 | 438 | Cs-137 | 1 | 250mci, 05-07-2002 | 2002-03-08 | HMV delivery line | Coal washery-2 | AERB/445/TAC/NG/07/017R-3/2002/22.85,Dt 8.3.2002 | In Use | Mr. B.Srinivas
17 | Endress Hauser | QG-100 | 1187 | Cs-137 | 1 | 7.4GBQ, 10-2004 | 2004-06-01 | HMC-1 delivery line | Coal washery-3 | AERB/RSD/NG-NR-250/2004/4548,Dt JUNE-2004 | In Use | Mr. B.Srinivas
18 | Endress Hauser | QG-100 | 1188 | Cs-137 | 1 | 7.4GBQ, 10-2004 | 2004-06-01 | HMC-2 delivery line | Coal washery-3 | AERB/RSD/NG-NR-250/2004/4548,Dt JUNE-2004 | In Use | Mr. B.Srinivas
19 | Endress Hauser | QG-100 | 1186 | Cs-137 | 1 | 7.4GBQ, 10-2004 | 2004-06-01 | HMC-3 delivery line | Coal washery-3 | AERB/RSD/NG-NR-250/2004/4548,Dt JUNE-2004 | In Use | Mr. B.Srinivas
20 | Endress Hauser | QG-100 | 1189 | Cs-137 | 1 | 11GBQ, 10-2004 | 2004-06-01 | HMV-1 delivery line | Coal washery-3 | AERB/RSD/NG-NR-250/2004/4548,Dt JUNE-2004 | In Use | Mr. B.Srinivas
21 | Endress Hauser | QG-100 | 1190 | Cs-137 | 1 | 11GBQ, 10-2004 | 2004-06-01 | HMV -2deleivery line | Coal washery-3 | AERB/RSD/NG-NR-250/2004/4548,Dt JUNE-2004 | In Use | Mr. B.Srinivas
22 | Scantech | COAL SCAN-2100 | 8147CN & 3967AR | Cs-137 & Am-241 | 2 | 0.185GBQ, 18.062008 & 3.7 GBQ,29.10.2007 | 2009 | Wash Coal Belt | Coal washery-3 | AERB/RSD/NG/NR 250/2009/9105 | In Use | Mr. DP Patel
23 | Scantech | COAL SCAN-2100 |  | Cs-137 & Am-241 | 2 | 0.185GBQ,18.062008 & 3.7 GBQ,29.10.2007 | 2009 | Wash Coal Belt | Coal washery-2 | AERB/RSD/NG/NR 250/2009/9105 | In Use | Mr. DP Patel
24 | Endress Hauser | QG-100 | RX 970 | Cs-137 | 1 | 7.4 GBq | NOT INSTALLED | KEPT IN STORE | NA | AERB/RSD/NG/NR 250/2009/7246 | In Store | Mr. DP Patel
44

## 17.03.2026
RSO meeting at SMS-3 Conference Room
Date & Time: -17.03.2026(4.00 PM - 5.00 PM)
Chaired By: - Mr. Lalit Kumar Goyal
Sl. No. | Name | Mail id | Mob. No. | Department | Attendance
1 | Lalit Kumar Goyal | lalit.goyal@jindalsteel.com | 9827477098 | CAC | P
2 | Dhirendra Prasad Kushwaha | dhirendra.kushwaha@jindalsteel.com | 8827477099 | CME & HESE | A
Certified Rso from Department
3 | Mandeep Rajput | mandeep.rajput@jindalsteel.com | 9109137541 | BF # 2 | P
4 | Bhishma Patel | bhisma.patel@jindalsteel.com | 8827427237 | BF-1
5 | Saurabh Tiwari | saurabh.tiwari@jindalsteel.com | 9425522401 | BF # 1
6 | Nikhilesh Gawhade | nikhilesh.gawhade@jindalsteel.com | 9109979148 | SMS # 3 | P
7 | Ritesh Rai | ritesh.rai@jindalsteel.com | 8827477306 | Sinter Plant
8 | Suraj Yadav | suraj.yadav@jindalsteel.com | 9109956841 | Plate Mill
9 | Sagar Vinayak Wanve | sagar.wanve@jindalsteel.com | 9109979042 | Plate Mill
10 | Kanhaiya Maurya | kanhiya.maurya@jindalsteel.com | 8827394930 | Power Plant
11 | Alok Agarwal | alok.agrawal@jindalsteel .in, | 9109130430 | TSD (BF# 2 - Lab) | P
12 | Simanchal Panda | simanchala.panda@jindalsteel.in, | 9109979088 | OHS - Representative
13 | Ranjeet Kumar | ranjeet.kumar1@jindalsteel.in, | 8827478305 | SMS # 3
14 | Hemnant pachori | hemant.pachori@jindalsteel.in, | 7400996393 | SMS # 2 | P
Radioactive status
SMS2 | 10 nos in use
SMS3 | 10 nos in use , 4 nos to be disposed
BF 2 | 6 nos in use
Minutes Of Meeting
Sl. No. | Meetings Points | Action Points | Target Date | Status | Action By | Remark
1 | Meeting Frequency | Monthly | 2nd Wednesday April 2026 |  | Simanchal Panda
2 | SSR report for July-Dec2025 | To be submitted in elora | 20.03.2026 |  | Simanchal Panda | TOP PRIORITY
3 | New RSO registration along with finalization of list | NFA to be raised | 17.03.2026 |  | Mandeep /nikhlesh | DEPT: SMS-2 , HEMANT PACHORY / COAL WASHERY/ SAFETY Mohan Iyer /Sahoo to be removed from portal as per RSO procedure.
3 | RSO -expiry | RSO to be exam | 17.03.2026 |  | Mandeep /nikhlesh | DEPT: SMS-2 , HEMANT PACHORY / COAL WASHERY/ SAFETY Mohan Iyer /Sahoo to be removed from portal as per RSO procedure.
6 | New Cobalt-60 to be procured for SMS-3 Combi caster and disposal of Cs-137 | 1. Extraction of old source rods from old shields & shifting to transport shield 2. Wipe test 3. Disposal | 10.04.2026 | 1.New cobalt procured and used. 2. SR to be prepared for disposal of old source | Mr. Nikhilesh & Mr. Ranjeet | Road map to be circulated.
9 | Survey Meter | caliberation certificate expiry of SMS2 so Hemant make SR | 20.03.2026 |  | Simanchal Panda | All RSO to be provided the details

## 23.03.2026
RSO meeting at SMS-3 Conference Room
Date & Time: -23.03.2026(3.00 PM - 5.00 PM)
Chaired By: - Mr. Lalit Kumar Goyal
Sl. No. | Name | Mail id | Mob. No. | Department | Attendance
1 | Lalit Kumar Goyal | lalit.goyal@jindalsteel.in | 9827477098 | CAC | P
Certified Rso from Department
2 | Mandeep Rajput | mandeep.rajput@jindalsteel.in | 9109137541 | BF # 2 | P
3 | Bhishma Patel | bhisma.patel@jindalsteel.in | 8827427237 | BF-1 | P
4 | Saurabh Tiwari | saurabh.tiwari@jindalsteel.in | 9425522401 | BF # 1 | L
5 | Nikhilesh Gawhade | nikhilesh.gawhade@jindalsteel.in | 9109979148 | SMS # 3 | P
6 | Ritesh Rai | ritesh.rai@jindalsteel.in | 8827477306 | Sinter Plant | P
7 | Suraj Yadav | suraj.yadav@jindalsteel.in | 9109956841 | Plate Mill
8 | Sagar Vinayak Wanve | sagar.wanve@jindalsteel.in | 9109979042 | Plate Mill
9 | Kanhaiya Maurya | kanhiya.maurya@jindalsteel.in | 8827394930 | Power Plant
10 | Alok Agarwal | alok.agrawal@jindalsteel .in, | 9109130430 | TSD (BF# 2 - Lab) | P
11 | Simanchal Panda | simanchala.panda@jindalsteel.in, | 9109979088 | OHS - Representative
12 | Ranjeet Kumar | ranjeet.kumar1@jindalsteel.in, | 8827478305 | SMS # 3
13 | Hemnant pachori | hemant.pachori@jindalsteel.in, | 7400996393 | SMS # 2 | P
Radioactive status
SMS2 | 10 nos in use
SMS3 | 10 nos in use , 4 nos to be disposed
BF 2 | 6 nos in use
Minutes Of Meeting
Sl. No. | Meetings Points | Action Points | Target Date | Status | Action By | Remark
1 | Meeting Frequency | Monthly | 2nd Wednesday April 2026 |  | Simanchal Panda
2 | SSR report for July-Dec2025 | To be submitted in elora | 20.03.2026 |  | Simanchal Panda | TOP PRIORITY
3 | New RSO registration along with finalization of list | NFA to be raised | 17.03.2026 |  | Mandeep /nikhlesh | DEPT: SMS-2 , HEMANT PACHORY / COAL WASHERY/ SAFETY Mohan Iyer /Sahoo to be removed from portal as per RSO procedure.
3 | RSO -expiry | RSO to be exam | 17.03.2026 |  | Mandeep /nikhlesh | DEPT: SMS-2 , HEMANT PACHORY / COAL WASHERY/ SAFETY Mohan Iyer /Sahoo to be removed from portal as per RSO procedure.
6 | New Cobalt-60 to be procured for SMS-3 Combi caster and disposal of Cs-137 | 1. Extraction of old source rods from old shields & shifting to transport shield 2. Wipe test 3. Disposal | 10.04.2026 | 1.New cobalt procured and used. 2. SR to be prepared for disposal of old source | Mr. Nikhilesh & Mr. Ranjeet | Road map to be circulated.
9 | Survey Meter | caliberation certificate expiry of SMS2 so Hemant make SR | 20.03.2026 |  | Simanchal Panda | All RSO to be provided the details

## Source
| Source | Equipment | Dispose
Plate Mill | 3 | 1 | 0
SMS-3 | 14 | 10 | 6 | 14
SMS-2 | 10 | 10 | 4 | 10
BF-1 | 2 | 2 |  | 2
BF-2 | 8 | 8 |  | 8
Sinter | 2 | 2 |  | 2
Coal Washry | 1 | 1 |  | 1
Power plant | 4 | 4 |  | 4
Total | 44 | 38 |  | 41
TSD | 2 | 2
| 46 | 40